Software Development Plan (SDP),
For

FLEXISAF EDUSOFT LIMITED
SAFHRMS

CONTRACT NUMBER: SAF_HRMS_001

Prepared for:
FlexiSAF EDUSOFT LIMITED

Prepared by:
FlexiSAF KANO
Suite D12, UMMI PLAZA, BEHIND JIFATU STORES, ZARIA ROAD,
 KANO NIGERIA

Authenticated by __________________	Approved by__________________

Date	___________________	Date	__________________

DOCUMENT APPROVAL
	NAME	DATE
Verified by: / Project Leader
Authenticated by: / Project Manager
Approved by: / Client

Archiving place: SAFSMS Managing Documents\SDP

Copies available: .docs, .pdf
REVISION HISTORY
REVISION	DESCRIPTION
A
B
C
D
E

Index	-	A	B	C	D	E
Written by
Verified by
Checked by
Authenticated by
Approved by

LIST OF EFFECTIVE PAGES

PAGES	REVISION	PAGES	REVISION

Table of Contents
1SCOPE	1
1.1Identification	1
1.2System Overview	1
1.3Document Overview	1
1.4Relationship to Other Plans	2
2REFERENCED DOCUMENTS	3
2.1Government Documents	3
2.2Non Government Documents	3
3SOFTWARE DEVELOPMENT MANAGEMENT	4
3.1Project Organization and Resources	4
3.1.1Contractor Facilities	4
3.1.2Client Furnished Equipment, Software and Services	6
3.1.3Organizational Structure	6
3.1.4Personnel	7
3.2Schedule and Milestone	8
3.2.1Activities	8
3.2.1.1Software Specification Phase	8
3.2.1.2Preliminary Design Phase	9
3.2.1.3Detailed Design Phase	9
3.2.1.4Implementation and Unit Testing Phase	10
3.2.1.5Integration & Testing Phase	10
3.2.1.6System Testing Phase	11
3.2.1.7Acceptance Testing/Deployment/Capacity Building Phase	11
3.2.2Source Identification	12
3.3Risk Management	12
3.4Security	13
3.5Interface with Associates Contractors	13
3.6Interface with Software IV & V Agent(s)	13
3.7Subcontractor Management	13
3.8Formal Reviews	13
3.9 Software Development Library	15
3.10Corrective Action Process	16
3.11Problem/Change Report	16

LIST OF FIGURES
Figure	Page
Figure 3.1: Organizational Structure	7
Figure 3.2: Software Development Library	15
Figure ‎5.1: Organization Structure for Formal Qualification Testing	22
Figure ‎6.1: Organizational Structure for Software Product Evaluation Activities	25
Figure 7.1: Flowchart of Configuration Control	32

LIST OF APPENDIES
Appendix	Page
A	Gantt Chart...	38
B	Work Breakdown Structure	39
C	PCR Form	40
D	Software Specification Review Checklist	41
E	Preliminary Design Review Checklist	43
F	Test Readiness Review Checklist	45

CHAPTER 1
SCOPE
This Software Development Plan is a part of the documentation prepared within the scope of the industrial implementation of DOD-STD-2167A. This chapter is divided into the following sections.
Identification
This section contains the approval identification number, title, and abbreviation of the system.
System Identification Number	: SAFHRMS
System Title	: SAF HUMAN RESOURCE MANAGEMENT SYSTEM
System Abbreviation	: SAFHRMS

System Overview
The SAFHRMS is intended to provide solutions for computing, managing staff’s activities in an organization and aids in documenting records easily in an automated way using SAFHRMS software. Which involves (Personnel Management, Benefits, Health and Safety, Workforce Management, Training), and other criteria for Human Resources applications
To achieve this, it shall be able to:
- Manage employee bio-data (Personal record).
- Manage Employee leaves, seminars, benefits, evaluation and administration.
- Offices Held by Employee
- Produce high level reports of staff’s record including memos, offer letters, promotion letters, leave letters, annual reports, customer relations and lots more.
- Create and manage users of the system and control levels of access to the system based on user roles.

Document Overview
The Software Development Plan (SDP) describes the contractor’s estimates for achieving the development of the software. This document is used to fully inform the client, the organizational setup and methods applied for the software development. This document also allows the client to control the procedures, management, and means implemented for software development.

Chapter 1	Describes the scope, identification, system overview, document overview and relationship to other plans.
Chapter 2	Referenced documents, government documents and non government documents.
Chapter 3	Defines the planning associated with software management activities.
Chapter 4	Defines the planning associated with software engineering activities.
Chapter 5	Defines the planning associated with formal qualification testing activities.
Chapter 6	Defines the planning associated with software product evaluation activities.
Chapter 7	Describes the software configuration management activities.
Chapter 8	Describes other software development functions.
Chapter 9	Notes.

Relationship to Other Plans
SAF-SMS

CHAPTER 2
REFERENCED DOCUMENTS
This chapter list by document number and title all documents referenced in this plan.
Government Documents
This section list all government documents referenced in this plan.

Non Government Documents
This section list all non government documents referenced in this plan.
[1]	Web References, more to be enlisted.
[2]	ADSU SRMS Document

CHAPTER 3
SOFTWARE DEVELOPMENT MANAGEMENT
This chapter is divided into the following sections to describe the planning associated with software development management activities.
Project Organization and Resources
This section is divided into the following sub paragraphs to describe the project organization and the project resources.
Facilities
This sub section provides description of the facilities to be used for the contracted effort.
Table 3.1 describes the hardware facilities that will be used in this project.
Table ‎3. Hardware Facilities
Hardware	Purpose	Number of unit	Location
Development Server	Software configuration, project management, system test environment	1	Office
Personal Computer (Laptops)	Documentation and Research, / Coding, / System test	6	Office
Printer	Document printing	1	Office
USB	Instant File Sharing	1	Office
Dongle (Modem)	Internet Service	2	Office

Table 3.2 Software facilities that will be used in this project.
Table ‎3. Software Facilities
Software	Purpose
Ubuntu Linux, Microsoft Windows (7 and above)	Project Development OS
Open Libre Office, Microsoft Office	Project Documentation
Microsoft Project	Project Planning and Tracking
Open Office, Microsoft PowerPoint 2010 and above	Project Presentation
Astah Professional	Project Diagram creation(UML)
MYSQL Workbanch	Modeling (ERD)
Bit bucket	Code Collaboration
Netbeans 8/Eclipse/JetBrain	IDE
Bugzilla	Issues and Bugs tracker
Balsamiq / Pencil /	UI Mock Ups

Table 3.3 Tools and Libraries
Table ‎3.3: Tools, Libraries and Technologies
Software	Purpose
Angular JS	UI and Ajax implementation
Java EE 7 (JPA 2, EJB 3.1)	Business Logic Implementation
Jasper Reports 5.0	Reporting Tool
MySql 5.1	RDBMS
JUnit 4.0	Module Unit Testing
FindBugs 1.3.9	Static Bug Analysis
Chrome/Moxilla Developer Tools	Debugging on the browser
Speed Tracer	Client-side speed optimization
Netbeans Profiler	Code optimization
Angular JSON parser	Client-Server side integration
JIRA	Project management, collaboration

Table 3.4 describes the workspace that will be used in this project.
Table ‎3.4: Workspace
Workspace	Purpose
FlexiSAF Kano Office	Documentation, discussion, coding and testing, review, meeting, testing and deployment.

Table 3.5 describes stationery that will be used in this project.
Table ‎3.5: Stationery
Stationery	Qty
A4 Paper	12 rims
Hard Cover Folders	5 units
Puncher	1 unit
CD-R	10 units
Marker Pen	5 units
Stapler	1 unit
Pack of pins	1 unit
White Board	1
Blue Board	2

Client Furnished Equipment, Software and Services
Deployment server and power backup would be provided by the client

Organizational Structure
This sub section describes the authority and responsibility of each organization. Figure 3.1 depicts the whole organizational structure.

Figure ‎3.: Organizational Structure
The following persons and activities are shown in Figure 3.1

Client Representative	:	FlexiSAF Edusoft Limited
Responsible for providing input and budget for the project.
Prime Contractor	:	FlexiSAF Tech Solutions Ltd
Responsible for overseeing the project to	completion successfully.
Software Project Team	:	FlexiSAF Software Development Team
Responsible for the software development activities of the SAFHRMS

Personnel
This sub section describes the total number of personnel necessary to complete the software development project as shown in Table 3.6.
Table ‎3.6: Personnel in ADSU SRMS project
Roles	Number of Persons
Project Manager (PM)	1
Project Leader (PL) and Lead Developer (LD)	2
Quality Manager (QM)	1
Configuration Manager (CM) and Communication Manager (CM)	2
Business Analyst(BA) and System Analyst (SA)	2
Total	8

Schedule and Milestone
This section is divided into the following sub sections.
Activities
This sub section describes each software development activity of the project and its associated schedule, based on the contract master schedule.
Software Specification Phase (SSP)
  This activity indicates the following:
Activity description
This phase is aimed to develop the Software Requirement Specification (SRS) for the SAFHRMS Project.
Activity duration
The duration of this phase takes 5 days.
Activity initiation
The work contract and technical requirements are extracted from the client in the form of interviews, questionnaires and meetings.
- Formal documentation
- Software Requirement Specification (SRS)
- Activity completion
- SRS completed and approved by Client.
- Software Specification Review (SSR)
Preliminary Design Phase (PDP)
  This activity indicates the following:
Activity description
This phase is aimed to define the architecture design of the system.
Activity duration
The duration of this phase takes4days.
Activity initiation
SRS completed and approved by Client.
Formal documentation
Preliminary Software Design Document (SDD), chapter 1-3.
- Activity completion
- Preliminary SDD, chapter 1-3 completed and approved by Project Manager and Client.
- Preliminary Design Review (PDR)
Detailed Design Phase
  This activity indicates the following:
Activity description
This phase is aimed to define the detailed design of the system.
Activity duration
The duration of this phase takes 8 days.
- Activity initiation
- Preliminary SDD, chapter 1-3 completed and approved by Project Manager and Client
- Preliminary Design Review (PDR)
- Formal documentation
- Software Design Documentation (SDD)
- Preliminary Software Test Description (STD)
- Activity completion
Completed SDD and Preliminary STD approved by Project Manager.

Implementation and Unit Testing Phase
  This activity indicates the following:
Activity description
This phase is aimed to code, debug and test the CSUs.
Activity duration
The duration of this phase takes 16 days.
Activity initiation
Complete SDD and Preliminary STD approved by Project Manager.
Formal and informal documentation
-
Activity completion
Source code completed.
Integration & Testing Phase
This activity indicates the following:
Activity description
This phase is aimed to integrate and test the CSC.
Activity duration
The duration of this phase takes 3 days.
Activity initiation
Source code completed.
- Formal and informal documentation
- Software Test Description (STD)
- Software Development Files (SDF)
- Activity completion
- The CSCs are integrated and tested.
- Complete STD and SDF completed and approved by Project Manager.
- Test Readiness Review (TRR)
System Testing Phase
  This activity indicates the following:
Activity description
This phase is aimed to test the overall system.
Activity duration
The duration of this phase takes 3 days.
Activity initiation
Complete STD and SDF completed and approved by Project Manager.

Formal and informal documentation
Software Test Result (STR)
- Activity completion
- The system is fully integrated and tested.
- STR completed and approved by the project manager

Acceptance Testing/Deployment/Capacity Building Phase
  This activity indicates the following:
Activity description
This phase is aimed to test and present the overall system to the client for acceptance.
Activity duration
The duration of this phase takes 9 days.
Activity initiation
Software Test Result (STR) approved by the project manager
- Formal documentation
- Activity completion
- The system is deployed and tested.
- STR completed and approved by Client.
- System deployed.
- Training conducted
Source Identification
This sub section identifies and describes the source of the required resources (software, and hardware) for this project. Please refer to sub section 3.1.1.
Risk Management
Table 3.7 describes the procedures for managing areas of risk to successful of project completion.
Table ‎3.7: Risk Management Description
Risks	Priority	Risk Mitigation plan	Contingency plan	Person in Charge
Not meeting the deadline	High	The schedule must be followed by team members; / daily internal meeting to report on project progress	The resources should be reassigned	Project Leader
Loss of data	High	Daily and weekly backup	Backup data on external hard drive and push it on bitbucket	Configuration Manager
Not meeting the requirement	High	The specification must be approved by QM	The issues should be discussed with the QM	Project Manager / Quality Manager and Project Leader
Medical or emergency leave	Medium	NA	The resources should be reassigned	Project Leader
Natural disaster	Low	Daily and weekly backup	Backup data on external hard drive	Configuration Manager
		NA	The project plan is discussed with the Client.	Project Manager and Project Leader

Security
Not applicable
Interface with Associates Contractors
Not applicable
Interface with Software IV & V Agent(s)
Not applicable
Subcontractor Management
Not applicable
Formal Reviews
Table 3.7 describes the internal procedures for preparing and conducting formal reviews.

Table ‎3.8: Formal Review Description
Formal Review	Description	Participant	Checking items	Date and Location
Software Specification Review	Review the software specification	Software Project Team and Client Representative	SRS	Xx/yy/2015 / FlexiSAF Office
Report Design Review	Review the design of the reports required for the system	Software Project Team and Client Representative	RDD	Xx/yy/2015 / FlexiSAF Office
Preliminary Design Review	Review the architecture design of the system	Software Project Team and Client Representative	SDD, Chapters 1-3	Xx/yy/2015 / FlexiSAF Office
Database Design Review	Review the database design of the system	Software Project Team	ERD	Xx/yy/2015 / FlexiSAF Office
Detailed Design Review	Review the detailed design of the system	Software Project Team	Complete SDD	Xx/yy/2015 / FlexiSAF Office
Test Readiness Review	Review the completed System	Software Project Team and	STD, SDF, source code	Xx/yy/2015 / FlexiSAF Office

 Software Development Library
The software development library of the project is depicted in Figure 3.2.
(To be effected)

Figure ‎3.: Software Development Library

Corrective Action Process
This section describes the corrective action process. The process can be started by the Client which must go through the Project Manager. Project Manager then assigns the changes to the Project Leader. If the processes start from the internal development team, then Project Leader will take necessary action to solve the changes. Figure 7.2 in chapter 7.3.1 (to be effected)shows the corrective action process.
Problem/Change Report
Refer Appendix C (Problem/Change Report)